## Weekly Plan
Week1 and 2 | Spring Boot /Spring Data,Mysql Integration,GitHub | LBConnect,Score Check, | Quiz
Week3 and 4 | Mongo Integration,Spring Email,Spring Batch
Week5 | Spring Cloud | API Gateway and Load Balancer | Quiz
Week6 | Spring Security | on All Service | Quiz
Week7 | Buffer
Week8 | Logging, Junit, Extra | Coverage for one service | Evaluation of Project
Week9 Wind Up Project --react

## Day Wise Updates
Day | Activity1 | Activity2 | Activity3 | Activity4 | Activity5
1 | Docker/Docker Hub installation | Git Hub Creation and introduction | Eclipse Installation | JIRA Introduction | Project Kick Start
2 | Spring Boot Explanation | Discuss Spring Data | REST API Explanation | Build SpringBoot REST Project
3 | Revise Spring Boot and Project Set Up | Build Lender |  | Write Controller and Service for Lender | POSTMAN
4 | Revise Lender,SpringBoot,Spring Data | Build Borrower,Loan Entitities
5 | Work on core logic after thorough discussion
6 | Decide All endpoints and core logic writtem
7 | Score Check Service Creation
8 | Integration of Score check with lbconnect App | create mongo db in docker using docker compose
9 | Discuss all scenarios and update
10 | Integration with mongo to view the data using end point
11 | mongo environment creation :Spring batch to move the data
12 | Discuss Spring email and MQ
13 | Complete email and lb connect interaction
14 | Discusss Micro service
15 | Build Service Registry
16 | Revise docker,MS, Architecture,Spring Cloud
17 | Register lbconnect with eureka
18 | Register loanhistory and score check with Eureka
19 | Learn Docker / Docker Hub
20 | Material
21 | Quiz
22 | Spring Cloud
23 | Spring Cloud

## JIRA
| Sprint1: Borrower/Lender REST APIs | STATUS | POINTS | ASSIGNEE |  | Sub Tasks
STORY | Defining Entities for Lbconnect | DONE | 2 | KUMAR | 1 | Installation Verification and Git | KUMAR
STORY | Create Entities for Borrowers and Lenders,Loans | DONE | 2 |  | 2 | Create Entity | KUMAR
STORY | End points creation for Lb Connect | DONE | 2 |  | 2.1 | Create Entities in Java and Test | KUMAR
STORY | Connection establishment between endpoints and Entities | DONE | 3 |  | 2.2 | Try DDL-AUTO Approach | KUMAR
STORY | Thorough discussion on different scenarions and score check Integration | DONE | 3 |  | 2.3 | Verify Entities from MySQL work Bench | RAVI
Sprint2
STORY | Mongo DB on docker | DONE | 1 | KUMAR
STORY | Spring boot integration with mongo and Mysql, Cron Jobs | DONE | 1 | KUMAR |  | Spring Batch
STORY | Spring boot App to retrieve history from Mongo | DONE | 1 | KUMAR |  | How to connect 2 different Spring boot
STORY | Spring batch integration | DONE | 2 | KUMAR
STORY | Rabbit MQ / Active MQ on Docker | DONE | 1 | KUMAR
STORY | Set Up and update LB Connect to publish messages into Queue | DONE | 1 | KUMAR
STORY | Put Approved loan details in Queue from Lb Connect | DONE | 1 | KUMAR
STORY | Read meesage from Queue then prepare Document(PDF) | DONE | 2 | KUMAR
STORY | Send email to Borrower using Spring Email | DONE | 2 | KUMAR
Sprint3
STORY | Implement Eureka | DONE | 2
STORY | Implement Eureka on All Service | DONE | 2
STORY | Learn Docker / Docker Hub | DONE | 1
STORY | Dockerization of lb connect | DONE | 1
STORY | Implement API Gateway on All Services | TODO | 2
STORY | Implement docker on Lb Connect 2 Instances | DONE | 1
STORY | Test All Services with All Spring cloud concepts | IN PROGRESS | 1
Sprint 4
STORY | Implement Spring Security on All Service |  | 2
STORY | Implement Swagger |  | 1
STORY | Implment JUNIT on lb connect |  | 1
STORY | Deployment on on AWS and test |  | 4
Sprint 5
STORY | Circuit Breaker Example |  | 2
STORY | JWT Example |  | 2
STORY | Kafka Example |  | 2
STORY | Buffer |  | 4

## Project
Borrower Entity | Java | DB
id | int | int
name | String | VARCHAR
dob | datetime | timestamp
email | String | Varchar
address | String | Varchar
nominee | String | Varchar
mobile | Long | bigint
score | int | int
eligibility | int | int
Active | Boolean | Boolean
Lender Entity
id | int | int
name | String | VARCHAR
email | String | VARCHAR
mobile | Long | bigint
Amount | int | int
Processing | int
Loans
id | int | int | L123
LID | int | int | I1
BID | int | int | K1
LNAME | String | VARCHAR | ICICI
BNAME | String | VARCHAR | Kumar
Amount | int | int | 1000000
Date | date | date
Paid | int | int | 0
Balance | int | int | 1000000
EMIS | int | int | 10
Paid EMIs | int | int | 0
Balance EMIs | int | int | 10
Emi Amount | int | int | 100000
Processing | int | int | 10000

## Work Assigments
Task | Research on Spring Data JPA
Questions | Steretype annotation
Basic Eclipse shortcuts
SOLID Principles
Spring Data JPA Annotations
Wrapper classes
unboxing and auto-boxing
Work Assigments
Spring RestTemplate,scorecheck App,Fix lbconnect
Spring-boot w/web -8
Spring Boot Data JPA --lbconnect | RDBMS vs NoSQL -- Research Item
Spring Boot Mongo --scorecheck | Rertyable - Research Iteam
Spring Batch --Batch | completable future,executor service - Research Iteam
Spring boot Web --lb connect | CRON - Research Item
Spring boot email --EMail | actuator --Research Item
Spring Rest Template --lbconnect/score-check | Spring boot 1.x vs SpringBoot 2.x s SpringBoot 3.x | Open Item
Eureka --put all the screenshots and notes | /@Query Example | Research Iteam
Spring Boot Email --Discuss again
Git merge,git PR
Sprint ceremonies

## DTOS
Borrower registrationDTO |  | ApplyLoan DTO/POST |  | Eligible Loans/GET
name | String |  |  | LenderId | int
dob | datetime |  |  | LenderName | String
email | String |  |  | Eligible Amount | int
address | String | id | int | Processing Fee | int
nominee | String | amount | int
mobile | Long | LenderId | int
salary | int
Aaadhaar number | int
Loans
id | int
LID | int
BID | int
LNAME | String
BNAME | String
Amount | int
Balance | int
EMIS | int
Paid EMIs | int
Balance EMIs | int
Emi Amount | int
Processing | int | payEMI | Transactions table
|  | Amount should not be <EMI | Transaction ID
not greater than balance
|  | IF customer paid extra,remaining balance will be into smaaller EMI | Paid Date
UTR
paid Amount
Loan ID