## Weekly Plan
Week1/2 | Spring Boot /Spring Data,Mysql Integration,GitHub | LBConnect | Quiz
Week3 | Mongo Integration | Loan History and Score Check
Week4 | Spring Email,Spring Batch | Email Sending | Quiz
Week5 | Buffer | Docker/Docker Hub
Week6 | Spring Security | on All Service | Quiz
Week7 | Spring Cloud | API Gateway and Load Balancer
Week8 | Logging, Junit, Extra | Coverage for one service | Evaluation of Project
Week9 Wind Up Project --react

## Day Wise Updates
Day | Activity1 | Activity2 | Activity3 | Activity4 | Activity5
1 | Docker/Docker Hub installation | Git Hub Creation and introduction | Eclipse Installation | JIRA Introduction | Project Kick Start
2 | Spring Boot Explanation | Discuss Spring Data | REST API Explanation | Build SpringBoot REST Project
3 | Revise Spring Boot and Project Set Up | Build Lender |  | Write Controller and Service for Lender | POSTMAN
4 | Revise Lender,SpringBoot,Spring Data | Build Borrower,Loan Entitities
5 | Work on core logic after thorough discussion
6 | Decide All endpoints and core logic writtem
7 | Discuss all scenarios and update
8 | Score Check Service Creation
9 | Integration of Score check with lbconnect App

## JIRA
| Sprint1: Borrower/Lender REST APIs | STATUS | POINTS | ASSIGNEE |  | Sub Tasks
STORY | Defining Entities for Lbconnect | DONE | 2 | KUMAR | 1 | Installation Verification and Git | KUMAR
STORY | Create Entities for Borrowers and Lenders,Loans | DONE | 2 |  | 2 | Create Entity | KUMAR
STORY | End points creation for Lb Connect | DONE | 2 |  | 2.1 | Create Entities in Java and Test | KUMAR
STORY | Connection establishment between endpoints and Entities | DONE | 3 |  | 2.2 | Try DDL-AUTO Approach | KUMAR
STORY | Through discussion on different scenarions and score check Integration | BACKLOG | 3 |  | 2.3 | Verify Entities from MySQL work Bench | RAVI

## Project
Borrower Entity | Java | DB
id | int | int
name | String | VARCHAR
dob | datetime | timestamp
email | String | Varchar
address | String | Varchar
nominee | String | Varchar
mobile | Long | bigint
score | int | int
eligibility | int | int
Active | Boolean | Boolean
Lender Entity
id | int | int
name | String | VARCHAR
email | String | VARCHAR
mobile | Long | bigint
Amount | int | int
Processing | int
Loans
id | int | int | L123
LID | int | int | I1
BID | int | int | K1
LNAME | String | VARCHAR | ICICI
BNAME | String | VARCHAR | Kumar
Amount | int | int | 1000000
Date | date | date
Paid | int | int | 0
Balance | int | int | 1000000
EMIS | int | int | 10
Paid EMIs | int | int | 0
Balance EMIs | int | int | 10
Emi Amount | int | int | 100000
Processing | int | int | 10000

## Work Assigments
Task | Research on Spring Data JPA
Questions | Steretype annotation
Basic Eclipse shortcuts
SOLID Principles
Spring Data JPA Annotations
Wrapper classes
unboxing and auto-boxing
Work Assigments | Can we store Employees and Departments in a single List?
Spring RestTemplate

## DTOS
Borrower registrationDTO |  | ApplyLoan DTO/POST |  | Eligible Loans/GET
name | String |  |  | LenderId | int
dob | datetime |  |  | LenderName | String
email | String |  |  | Eligible Amount | int
address | String | id | int | Processing Fee | int
nominee | String | amount | int
mobile | Long | LenderId | int
salary | int
Aaadhaar number | int
Loans
id | int
LID | int
BID | int
LNAME | String
BNAME | String
Amount | int
Balance | int
EMIS | int
Paid EMIs | int
Balance EMIs | int
Emi Amount | int
Processing | int